## Forgot password
Feature | Forgot password | [10 empty] | Passed
Test requirement | Have email | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 2 | 0 | 0 | 0
Round 2 | 2 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Forgot password | Forgot password
FP01 | When user forgot password, user will click "forgot password" button to get password Email has in system | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Login" category. 4. Click on "Forgot password" button. 5. Fill in email 6. Send code 7. Fill code and submit 8. Enter new password and confirm new password 9. Submit | The system will notifiy that "account had password" |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
FP02 | When user forgot password, user will click "forgot password" button to get password Email has not in system | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Login" category. 4. Click on "Forgot password" button. 5. Fill in email 6. Send code | The system will notifiy that "This email does not exists" |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy

## Authen and Author
Feature | Authen and authorization | [10 empty] | Passed
Test requirement | Having an email and password for Sign In. Having accounts : Customer :account: user, password: 123456 (valid) Account invalid: user1234, password: 2eoi12onzc(invalid) | [10 empty] | Failed
Number of TCs | 3 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 3 | 0 | 0 | 0
Round 2 | 3 | 0 | 0 | 0
Round 3 | 1 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Login | Login
AAA01 | Login successfully as Customer by username/email and password | 1. Access into website. 2. Click on guest symbol. 3. Click on "Login" category. 4. Input one of two text-boxes the "Username/Email" and "Password" or no any text box. (Account valid) 5. Click on "Login" button | The page redirects to the home page with the information of account that is signed in. The guest symbol is changed to the avatar symbol. | account(username/email) and password is required | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
AAA02 | Login fail as Customer by username/email and password invalid | 1. Access into website. 2. Click on guest symbol. 3. Click on "Login" category. 4. Input one of two text-boxes the "Username/Email" and "Password" or no any text box. (Account invalid) 5. Click on "Login" button | The message "Account or password not invalid!. | account(username/email) and password is required | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
Logout
AA03 | Testing algoriithm of the Loging out Function | 1. Access into website and sign in with an account. 2. Click on Avatar symbol in header of home page. 3. Click on "Logout" category. | The information of account that was saved in the page is must deleted | Have logged into a customer's account | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed

## Login By Google
Feature | Login by google | [10 empty] | Passed
Test requirement | Having an Google account for Log In. | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 2 | 0 | 0 | 0
Round 2 | 2 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Login by Google | Login by Google
LBG01 | Testing vewing when click "Login by google" button when in the Sign Ip Page | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Login" category. 4. Click on "Login by google" button. | The following form is exist |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
LBG02 | Testing agorithm of the signing in by google function-Successful | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Login" category. 4. Click on "Login by google" button. | The page redirects to the home page with the information of account that is signed in. The guest symbol is changed to the avatar symbol. |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy

## Register
Feature | Register | [10 empty] | Passed
Test requirement | Browser | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 2 | 0 | 0 | 0
Round 2 | 2 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Register | Register
RG01 | When guess want to create account to access system, buy timeshare But not fill in username, password, confirm password | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Sign up" category. 4. Fill email 5. Send code 6. Fill Code 7. Fill information (excep username) | Guess will not click button submit until guess must fill all information |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
RG02 | When guess want to create account to access system, buy timeshare But all information | 1. Access into website. 2. Click on Guest symbol in header of home page. 3. Click on "Sign up" category. 4. Fill email 5. Send code 6. Fill Code 7. Fill information (excep username) 8. Submit 9. Fill information visa 10. Submit | The system will show notify "register successfully" |  | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy

## Create project
Feature | Create project | [10 empty] | Passed
Test requirement | Browser | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 3 | 0 | 0 | 0
Round 2 | 3 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Create project | Create project
CP01 | When admin want create project of a timeshare But not fill information (project name, images, thumbnail, feature, attractions, description) | 1. Click create project button 2. Choose type project, building status, location 3. Submit | System wil show error,requrie must fill all information | 1.Login with role admin | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
CP02 | When admin want create project of a timeshare, fill all information | 1. Click create project button 2. Fill all information 3. Submit | System will show successfully create project | 1.Login with role admin | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
CP03 | When admin want create project of a timeshare All fill information, but duplication project name | 1. Click create project button 2. Fill all information 3. Submit | System wil show error "Project name duplicatie" | 1.Login with role admin | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy

## Create typeroom
Feature | Create typeroom | [10 empty] | Passed
Test requirement | Have project, and login role admin | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 2 | 1 | 0 | 0
Round 2 | 3 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Create typeroom | Create typeroom
CT01 | When admin want create typeroom of a project But not fill information (typeroom name, images, amenities, description) | 1. Click list project button 2. Click action of a project and choose create type room 3. Fill information (except typeroom name, images, amenities, description) 3. Submit | System wil show error,requrie must fill all information | 1.Login with role admin 2. Have Project | Failed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy | Because show error quickly
CT02 | When admin want create typeroom of a project, fill all information | 1. Click list project button 2. Click action of a project and choose create type room 3. Fill information 3. Submit | System will show successfully create typeroom | 1.Login with role admin 2. Have Project | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy
CT03 | When admin want create typeroom of a project All fill information, but duplication typeroom name | 1. Click list project button 2. Click action of a project and choose create type room 3. Fill information 3. Submit | System wil show error "typeroom name duplicatie" | 1.Login with role admin 2. Have Project | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy

## Create timeshare
Feature | Create timeshare | [10 empty] | Passed
Test requirement | Have project, have type room, login role staff | [10 empty] | Failed
Number of TCs | 2 | [10 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [7 empty] | N/A
Round 1 | 2 | 0 | 0 | 0
Round 2 | 2 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Note
Create timeshare | Create timeshare
CT01 | When admin want create timeshare of a project Not fill startdate, endate, price | 1. Click list project button 2. Click action of a project and manage typeroom 3. Click typeroom choose create timeshare 4. Fill information (except startdate, endate, price) 3. Submit | System wil show error "please fill all information" | 1.Login with role staff 2.Have project 3. Have TypeRoom | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy | Because show error quickly
CT02 | When admin want create timeshare of a project Fill all information, but project have not reservation info | 1. Click list project button 2. Click action of a project and manage typeroom 3. Click typeroom choose create timeshare 4. Fill information 3. Submit | System wil show error "Typeroom does not belong to project that have reservaion info" | 1.Login with role staff 2.Have project 3. Have TypeRoom | Passed | 2024-03-17 | Nguyen Mai Viet Vy | Passed | 2024-03-17 | Vy | Because show error quickly